VOXMERCH

Launch Action Plan

April 4 – June 30, 2026

The complete go-to-market playbook for taking VoxMerch from pre-launch buzz to live activations. Covers 58 days of social media, launch day coordination, and a full month of sales outreach, PR, events, email, and paid media through the end of June.

# Table of Contents

1. Executive Summary

2. Launch Timeline Overview

3. Pre-Launch Phase: April 4 – May 31 (58 Days)

3.1  Social Media Posting Cadence by Platform

3.2  58-Day Pre-Launch Social Media Schedule

3.3  Pre-Launch Sales Outreach

3.4  Brand Refresh Integration

3.5  Website and Conversion Optimization

4. Launch Week: June 1 – June 7

5. Post-Launch Phase: June 1 – June 30

5.1  June Social Media Posting Schedule

5.2  Sales Outreach Expansion

5.3  PR and Media Strategy

5.4  Email Campaign Sequences

5.5  Event Demos and Activations

5.6  Paid Media Strategy

6. Content Creation Requirements

7. Key Milestones and Deadlines

8. Success Metrics and KPIs

# 1. Executive Summary

VoxMerch turns attendee voices into one-of-a-kind art and custom merchandise in minutes, right on the show floor. It is not just a product demo. It is an experience people remember, talk about, and wear home. The platform also delivers client-ready engagement insights, making every activation measurable.

This action plan maps out a 58-day pre-launch runway (April 4 through May 31) built around building awareness, generating demo signups, and warming the accounts that matter most. It then carries into a full 30-day post-launch push through June 30, 2026, with coordinated sales, PR, email, events, and paid media working together from day one.

## Who We Are Reaching

Distributors: Branded merchandise distributors (e.g., HALO account executives) who want to offer their clients something no one else has

Activation Agencies: Event activation agencies looking for a turnkey, crowd-stopping experience they can white-label for their brand clients

## Where We Stand Today

Website is live and operational

10 pre-launch teaser posts with graphics are ready for LinkedIn, Instagram, and Facebook

Brand refresh is in progress, expected completion mid-May 2026

Pre-launch sales conversations are underway with select HALO account executives and one event activation company

Moderate paid media budget ($2K+) is allocated for launch amplification

## What Winning Looks Like

Pre-Launch: Get VoxMerch on the radar of distributors and agencies before anyone else does. Build an audience. Drive demo requests.

Launch Day: Create a coordinated moment across social, email, PR, and paid that makes June 1 feel unmissable.

Post-Launch: Convert warm leads into demos, demos into proposals, and proposals into signed deals. Fill the pipeline for Q3 event season.

# 2. Launch Timeline Overview

The launch is organized into three phases, each with a clear objective and escalating intensity.

| Phase | Dates | Duration | Primary Objective |
| --- | --- | --- | --- |
| Pre-Launch | April 4 – May 31 | 58 days | Build awareness, grow the audience, generate demo signups, warm target accounts |
| Launch Week | June 1 – June 7 | 7 days | Maximum visibility across all channels; create urgency and land the first conversions |
| Post-Launch GTM | June 8 – June 30 | 23 days | Sustain momentum, expand the pipeline, close early deals, capture testimonials |

## Critical Path Dependencies

| Milestone | Deadline | Why It Matters |
| --- | --- | --- |
| Brand refresh complete | May 15 | Everything published after this date carries the new identity |
| Updated website with new brand | May 20 | Refreshed visuals must be live before paid traffic starts driving visitors |
| Launch day content batch finalized | May 25 | All social posts, email copy, and PR assets locked and loaded |
| Paid media campaigns built | May 28 | Ad creative, targeting, and budgets loaded into LinkedIn and Meta |
| Press release distributed (embargoed) | May 29 | Gives journalists lead time to prepare coverage for June 1 |
| Official Launch | June 1 | All channels go live at once |

# 3. Pre-Launch Phase: April 4 – May 31 (58 Days)

The pre-launch window is about showing up consistently before anyone expects us to. We start building a social presence from scratch, warm up target accounts through direct outreach, and prepare every asset needed for launch day. The 10 existing teaser posts are distributed strategically across this window and supplemented with new content to keep the cadence steady.

## 3.1 Social Media Posting Cadence by Platform

The cadence below balances visibility with content quality. Because VoxMerch is building a social presence from zero, the first four weeks prioritize consistency over volume. Frequency ramps as June 1 approaches.

| Platform | Weeks 1–4 (Apr 4–May 1) | Weeks 5–6 (May 2–May 15) | Weeks 7–8 (May 16–May 31) | Total Pre-Launch Posts |
| --- | --- | --- | --- | --- |
| LinkedIn | 2x/week | 3x/week | 4x/week | 22–24 posts |
| Instagram | 3x/week | 4x/week | 5x/week | 30–34 posts |
| Facebook | 2x/week | 3x/week | 3x/week | 20–22 posts |

### Platform-Specific Approach

LinkedIn: This is where distributors and agency decision-makers pay attention. Lead with outcomes and business value. Keep the tone confident and conversational, not corporate. Best formats: short videos of the activation in action, carousels that walk through the voice-to-merch process, and thought leadership on where event engagement is headed.

Instagram: Visual-first, energy-first. Show the art. Show the merch. Show the crowd reaction. Reels (15–30 seconds) drive the most reach. Stories work well for daily countdown touchpoints during the ramp-up weeks. Let people feel what it is like to be at the booth.

Facebook: Cross-post the strongest LinkedIn and Instagram content with platform-appropriate adjustments. Use Facebook for community building and engagement in event industry groups. Video consistently outperforms static images here.

## 3.2 58-Day Pre-Launch Social Media Schedule

Below is the full day-by-day posting schedule. Posts marked with an asterisk (*) are one of the 10 existing teaser posts. All other posts need to be created. Everything published after May 15 should use the refreshed brand identity.

### Week 1: April 4 – April 10 // Introduce the Brand

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Apr 4 | Fri |  | Teaser #1* – "Something is about to change" |  |
| Apr 6 | Sun |  | Behind-the-scenes: First look at AI-generated art |  |
| Apr 7 | Mon | Teaser #1* – Meet VoxMerch (brand intro) |  | Meet VoxMerch (cross-post LI) |
| Apr 8 | Tue |  | Reel: 15 sec – watch a voice become a t-shirt |  |
| Apr 9 | Wed |  |  |  |
| Apr 10 | Thu | "Event merch hasn't evolved in a decade. We're changing that." | Carousel: Before and after – voice to finished art | "Event merch hasn't evolved" (cross-post LI) |

### Week 2: April 11 – April 17 // Name the Problem

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Apr 11 | Fri |  | Reel: "What if your voice became wearable art?" |  |
| Apr 13 | Sun |  | Story poll: "Best event swag you have ever received?" |  |
| Apr 14 | Mon | Teaser #2* – The real cost of forgettable event merch |  | Teaser #2* (cross-post LI) |
| Apr 15 | Tue |  | Teaser #3* – Visual teaser: finished merch showcase |  |
| Apr 16 | Wed |  |  |  |
| Apr 17 | Thu | The data on event engagement (and why most booths miss it) | Carousel: 5 reasons merch makes or breaks your booth | Event engagement data (cross-post LI) |

### Week 3: April 18 – April 24 // Show the Solution

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Apr 18 | Fri |  | Reel: How VoxMerch works in 30 seconds |  |
| Apr 20 | Sun |  | "Imagine your voice as a one-of-a-kind tee" |  |
| Apr 21 | Mon | Teaser #4* – From voice to merch: the VoxMerch experience |  | From voice to merch (cross-post LI) |
| Apr 22 | Tue |  | Carousel: Step by step through an activation |  |
| Apr 24 | Thu | The intersection of AI and live events is here | Teaser #5* – Art sample showcase | AI meets live events (cross-post LI) |

### Week 4: April 25 – May 1 // Build Credibility

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Apr 25 | Fri |  | Reel: Booth setup time-lapse concept |  |
| Apr 27 | Sun |  | Story: "What would YOUR voice look like as art?" |  |
| Apr 28 | Mon | Teaser #6* – What early partners are saying |  | Teaser #6* (cross-post LI) |
| Apr 29 | Tue |  | Carousel: Speed, quality, insights – VoxMerch by the numbers |  |
| May 1 | Thu | "June 1 is the day. The countdown starts now." | Teaser #7* – Official countdown begins | Official countdown (cross-post LI) |

### Week 5: May 2 – May 8 // Go Deeper

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| May 2 | Fri | How VoxMerch delivers post-event insights your clients actually use | Reel: "This is what the future of event merch looks like" |  |
| May 4 | Sun |  | Story: 30-day countdown graphic |  |
| May 5 | Mon | Teaser #8* – Spotlight: client-ready engagement insights | Carousel: 3 ways VoxMerch turns a booth into a business outcome | Client insights spotlight (cross-post LI) |
| May 6 | Tue |  | Reel: Voice recording to finished product in real time | Behind-the-scenes video (cross-post IG) |
| May 7 | Wed | For distributors: why VoxMerch is the offering your clients don't know they need yet |  |  |
| May 8 | Thu |  | Teaser #9* – Product demo preview | Why distributors need this (cross-post LI) |

### Week 6: May 9 – May 15 // Last Week Before Brand Refresh

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| May 9 | Fri |  | Reel: The energy of a live activation (montage) |  |
| May 11 | Sun |  | Story: "Rate this merch" interactive poll |  |
| May 12 | Mon | How event activation agencies can white-label VoxMerch for their clients | Carousel: Agencies vs. brands – two ways to work with us | Agencies and VoxMerch (cross-post LI) |
| May 13 | Tue |  | Reel: The fun factor – people love this booth | Fun factor video (cross-post IG) |
| May 14 | Wed | Teaser #10* – The last teaser before everything changes |  |  |
| May 15 | Thu |  | "New look. Same magic." – Brand refresh reveal | Brand refresh reveal (cross-post IG) |

NOTE: May 15 marks the brand refresh completion. All content from this point forward uses the new visual identity: updated logo, refreshed color palette, and the elevated energy that reflects what it actually feels like to be at a VoxMerch booth.

### Week 7: May 16 – May 22 // New Look, Full Energy

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| May 16 | Fri | "We cleaned up nice." – Introducing the refreshed VoxMerch | Reel: Brand reveal with new visuals in motion | Brand refresh announcement (cross-post LI) |
| May 17 | Sat |  | Story: Walk through the new brand assets |  |
| May 18 | Sun |  | Carousel: Then vs. now – the brand evolution |  |
| May 19 | Mon | "See VoxMerch in action before we go live." – Book a demo | Reel: Full product walkthrough, new brand | Book a demo (cross-post LI) |
| May 20 | Tue |  | "15 days to launch" countdown graphic |  |
| May 21 | Wed | Where experiential marketing is headed (and why it matters for your next event) | Story: Day-in-the-life of launch prep |  |
| May 22 | Thu | For distributors: the revenue opportunity behind VoxMerch | Carousel: What distributors earn with VoxMerch | Revenue opportunity (cross-post LI) |

### Week 8: May 23 – May 31 // Final Countdown

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| May 23 | Fri | "One week out. Here is what happens June 1." | Reel: Final countdown hype video | One week out (cross-post LI) |
| May 24 | Sat |  | Story: Behind-the-scenes launch prep |  |
| May 25 | Sun |  | Carousel: "5 things to know about VoxMerch before launch" |  |
| May 26 | Mon | "Why we built this" – the origin story | Reel: Founder message or team intro | Origin story (cross-post LI) |
| May 27 | Tue |  | "5 days out" countdown with product preview | Countdown (cross-post IG) |
| May 28 | Wed | Last call: lock in a launch week demo before spots fill up | Story: Daily countdown continues |  |
| May 29 | Thu | "This Sunday changes everything." | "3 days" countdown + sneak peek | Launch eve tease (cross-post LI) |
| May 30 | Fri |  | Reel: "Tomorrow is the day" hype reel | "Tomorrow" countdown (cross-post IG) |
| May 31 | Sat | "See you tomorrow." | "It is here." Eve post + Story blitz | Eve post (cross-post LI) |

## 3.3 Pre-Launch Sales Outreach

Direct outreach runs alongside the social schedule. The goal is straightforward: by launch day, target accounts should already know what VoxMerch is and have a reason to pay attention when we go live.

| Week | Activity | Target | Deliverable |
| --- | --- | --- | --- |
| Weeks 1–2 | Continue HALO AE outreach; follow up with the activation agency already in conversation | 5–8 HALO AEs + 1 activation agency | Personalized emails with product overview deck |
| Weeks 3–4 | Second touch: share teaser content, invite them to see a demo | Same accounts + 3–5 new HALO AEs | Demo invite email with calendar link |
| Week 5 | Deliver demos to everyone who raised a hand | Warm leads from Weeks 1–4 | Live product demo via Zoom or Teams |
| Weeks 6–7 | Expand outreach to additional event activation agencies | 3–5 new agencies | Tailored pitch focused on white-label partnership |
| Week 8 | Pre-launch urgency: "Be among the first to activate with VoxMerch" | All warm leads | Launch preview email with early access offer |

## 3.4 Brand Refresh Integration

The brand refresh lands mid-May. The timeline below keeps the transition clean without interrupting the content cadence.

| Date Range | What Happens |
| --- | --- |
| April 4 – May 14 | All content uses the current brand identity. Deploy the 10 existing teaser posts during this window. |
| May 10 – May 14 | Receive final brand assets from the design team. Begin creating the first batch of post-refresh content. |
| May 15 | Brand refresh goes live. Update social media profile photos, banners, and bios across LinkedIn, Instagram, and Facebook. |
| May 15 – May 16 | Post the brand refresh reveal content ("New look. Same magic." / "We cleaned up nice."). |
| May 17 – May 20 | Update the website with refreshed visuals, updated copy, and the elevated energy and fun that reflects what draws people to the booth. |
| May 20 – May 31 | All new content carries the refreshed brand. Sales deck, one-pager, and email templates updated to match. |

## 3.5 Website and Conversion Optimization

The website is live, which means the pre-launch window is the time to make sure it converts before paid traffic starts driving visitors to it.

Demo CTA: Add a clear, prominent way to book a demo from the homepage. Make it obvious, not buried.

Tracking: Install LinkedIn and Meta tracking pixels plus Google Analytics before any paid campaigns launch. This needs to be done well before May 28.

Launch Landing Page: Build a dedicated launch landing page with a countdown, a concise value prop, and a single CTA: book a demo.

Brand Refresh: The website must reflect the refreshed brand by May 20, before paid media starts sending traffic.

Mobile: Confirm mobile responsiveness. Event industry professionals browse heavily on their phones.

# 4. Launch Week: June 1 – June 7

This is the highest-energy stretch of the entire plan. Every channel fires at once. The goal is to make June 1 feel like an event in itself, not just an announcement.

## Launch Day: June 1 (Sunday)

LinkedIn: "VoxMerch is live. Voices in. Art and merch out. See it for yourself." (all 3 platforms)

Instagram: Launch Reel (60 sec product showcase) + Story blitz (5–7 Stories throughout the day) + feed post with launch graphic

Facebook: Launch video pinned to the top of the page

Email Blast: Launch announcement to the full contact list with a single clear CTA: book a demo

PR: Press release distributed to event industry trade publications and local business media

Paid: LinkedIn and Meta ad campaigns activated with launch creative

## Launch Week Day-by-Day: June 2 – June 7

| Date | Day | LinkedIn | Instagram | Facebook | Other Channels |
| --- | --- | --- | --- | --- | --- |
| Jun 2 | Mon | "Day 1: done." Recap + early traction | Reel: Launch day energy compilation | Recap post (cross-post LI) | Email to non-openers: "You missed something good" |
| Jun 3 | Tue | How VoxMerch works for distributors (deep dive) | Carousel: The activation experience, step by step | How it works (cross-post LI) | Sales: Follow up every launch-day demo request |
| Jun 4 | Wed | "Event merch will never be the same. Here is why." | Story: Live Q&A with audience questions |  | PR: Follow up with journalists |
| Jun 5 | Thu | The distributor opportunity: new revenue, no inventory risk | Reel: Booth reactions – the fun is real | Revenue opportunity (cross-post LI) | Email: Feature spotlight to segmented list |
| Jun 6 | Fri | "Week 1 in the books." Milestone post | Carousel: Week 1 highlights | Week 1 highlights (cross-post IG) | Sales: Second touch to warm leads |
| Jun 7 | Sat |  | Story: Weekend recap + "More coming next week" |  |  |

# 5. Post-Launch Phase: June 1 – June 30

Launch week creates the spark. June keeps it burning. The full month sustains momentum through consistent social posting, expanded sales outreach, PR and media activity, email nurture sequences, event demos, and paid media amplification.

## 5.1 June Social Media Posting Schedule

### June Posting Cadence

| Platform | June Frequency | Weekly Posts | Monthly Total |
| --- | --- | --- | --- |
| LinkedIn | 4–5x/week | 4–5 | 18–22 |
| Instagram | 5–7x/week (feed + Reels + daily Stories) | 5–7 feed/Reels | 22–30 |
| Facebook | 3–4x/week | 3–4 | 13–17 |

### Week 2: June 8 – June 14 // Educate and Convert

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Jun 8 | Sun |  | Reel: "Here is what attendees say at the booth" |  |
| Jun 9 | Mon | First activation results (case study format) | Carousel: Activation results infographic | First results (cross-post LI) |
| Jun 10 | Tue | "3 ways VoxMerch outperforms traditional event merch" | Reel: Side-by-side comparison | 3 ways (cross-post LI) |
| Jun 11 | Wed | Agency partnership spotlight | Story: Agency use case walkthrough |  |
| Jun 12 | Thu | The ROI of one VoxMerch activation, broken down | Carousel: ROI by the numbers | ROI breakdown (cross-post LI) |
| Jun 13 | Fri | Open Q&A: What do you want to know about VoxMerch? | Reel: Creative merch designs showcase | Q&A recap (cross-post LI) |
| Jun 14 | Sat |  | Story: "Design your dream merch" engagement prompt |  |

### Week 3: June 15 – June 21 // Social Proof and Partnerships

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Jun 15 | Sun |  | Reel: Watch the AI create unique art from a voice recording |  |
| Jun 16 | Mon | Partner spotlight: Event activation agency feature | Carousel: How the partnership model works | Partner spotlight (cross-post LI) |
| Jun 17 | Tue | Where experiential marketing is headed (and where VoxMerch fits) | Reel: "The activation that pays for itself" | Experiential trend piece (cross-post LI) |
| Jun 18 | Wed | Early adopter testimonial | Story: Customer highlight |  |
| Jun 19 | Thu | "How distributors add VoxMerch to their lineup" | Carousel: Distributor onboarding in 3 steps | Distributor onboarding (cross-post LI) |
| Jun 20 | Fri | The future of the show floor: creative, personal, measurable | Reel: Event energy compilation | Future of the show floor (cross-post LI) |
| Jun 21 | Sat |  | Story: Behind-the-scenes team content |  |

### Week 4: June 22 – June 28 // Close the Month Strong

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Jun 22 | Sun |  | Reel: "Your brand. Their voice. Merch they actually keep." |  |
| Jun 23 | Mon | "One month in. Here is what we have learned." | Carousel: Month 1 by the numbers | Month 1 update (cross-post LI) |
| Jun 24 | Tue | Feature deep-dive: the client insights dashboard | Reel: Insights dashboard walkthrough | Feature deep-dive (cross-post LI) |
| Jun 25 | Wed | "Q3 event season is coming. VoxMerch is ready." | Story: Upcoming event season teaser |  |
| Jun 26 | Thu | Customer success story: one activation, start to finish | Carousel: Before / during / after activation | Customer story (cross-post LI) |
| Jun 27 | Fri | "Here is what is coming in July" – roadmap preview | Reel: Sneak peek at what is next | What is next (cross-post LI) |
| Jun 28 | Sat |  | Story: "Thank you for an incredible first month" |  |

### Final Days: June 29 – June 30

| Date | Day | LinkedIn | Instagram | Facebook |
| --- | --- | --- | --- | --- |
| Jun 29 | Sun |  | Reel: Month 1 highlight reel |  |
| Jun 30 | Mon | "June, wrapped." Milestones, gratitude, and what is ahead | Carousel: June recap + July preview | June wrap-up (cross-post LI) |

## 5.2 Sales Outreach Expansion

Post-launch, sales shifts from warming to closing. The focus is converting the pre-launch leads who already know us while expanding outreach to new prospects who are seeing VoxMerch for the first time through our launch push.

| Week | Focus | Activity | Target Volume |
| --- | --- | --- | --- |
| June 1–7 | Convert warm leads | Follow up every demo request from launch week. Schedule demos within 48 hours of request. | All inbound + 10–15 warm accounts |
| June 8–14 | Broaden HALO reach | Expand to additional HALO account executives beyond the initial select group | 15–20 new HALO AEs |
| June 15–21 | Build the agency pipeline | Targeted outreach to 5–10 event activation agencies with the partnership pitch deck | 5–10 agencies |
| June 22–30 | Accelerate pipeline | Second and third touch sequences; deliver proposals to qualified opportunities; negotiate early deals | All active pipeline |

### Sales Collateral Needed for June

Product demo deck (updated with refreshed brand)

One-pager for distributors: focused on the revenue opportunity and how to add VoxMerch to their lineup

One-pager for activation agencies: focused on the white-label partnership model

ROI summary or value calculator for post-demo follow-up

Objection handling quick-reference for the most common distributor and agency pushbacks

## 5.3 PR and Media Strategy

| Timing | Activity | Details |
| --- | --- | --- |
| May 25–29 | Press release preparation | Draft and finalize the launch press release. Send embargoed copies to priority media contacts by May 29. |
| June 1 | Press release distribution | Distribute via PR wire + direct pitches to event industry trade publications: BizBash, Event Marketer, Exhibitor, Trade Show News Network |
| June 1–7 | Media follow-up | Personal follow-up with 10–15 journalists and editors at trade publications. Offer exclusive demo access. |
| June 8–14 | Byline and guest post pitches | Pitch a thought leadership article to 2–3 event industry publications on the role of AI in experiential marketing |
| June 15–21 | Podcast and webinar outreach | Pitch the VoxMerch founder as a guest on 3–5 event industry podcasts or webinar panels |
| June 22–30 | Earned media follow-up | Follow up on all outstanding pitches. Share any published coverage across social channels. |

## 5.4 Email Campaign Sequences

### Sequence 1: Launch Announcement (June 1–3)

| Email | Timing | Subject Line Direction | CTA |
| --- | --- | --- | --- |
| Email 1 | June 1 (launch day) | "VoxMerch is live: voices in, art and merch out" | Book a demo |
| Email 2 | June 2 | "See what you missed" (non-openers of Email 1) | Watch the product video |
| Email 3 | June 3 | "30 seconds that will change how you think about event merch" (non-clickers) | Book a demo |

### Sequence 2: Nurture and Educate (June 8–22)

| Email | Timing | Subject Line Direction | CTA |
| --- | --- | --- | --- |
| Email 1 | June 8 | "How one activation turns into months of engagement" | Read the case study |
| Email 2 | June 12 | "The numbers behind a VoxMerch activation" | See the ROI breakdown |
| Email 3 | June 16 | "Event agencies are paying attention. Here is why." | Explore the partnership model |
| Email 4 | June 22 | "Your Q3 event calendar just got more interesting" | Book a demo |

### Sequence 3: Re-engagement (June 25–30)

| Email | Timing | Subject Line Direction | CTA |
| --- | --- | --- | --- |
| Email 1 | June 25 | "Still thinking it over? Here is what is new." | Book a demo |
| Email 2 | June 30 | "Month 1 results are in" (social proof + momentum)" | Schedule a call |

## 5.5 Event Demos and Activations

Live demos are the single strongest sales tool VoxMerch has. The product is experiential by nature. The fun and energy of the booth is what draws people in, and seeing the voice-to-art-to-merch process firsthand is the fastest path from curiosity to commitment.

| Week | Activity | Details |
| --- | --- | --- |
| June 1–7 | Virtual demo blitz | Offer 15–30 minute live demos via Zoom to all warm leads and launch-week inbound requests. Target 8–12 demos this week. |
| June 8–14 | In-person demo opportunity | Identify one local event or trade show where VoxMerch could do a live pop-up activation. Even a small-scale demo creates video content and social proof. |
| June 15–21 | Partner co-demo | Invite the event activation company already in conversation to co-host a joint demo or webinar for their client base. |
| June 22–30 | Capture demo content | Record and edit demo footage for use in July sales outreach, social content, and the website. |

## 5.6 Paid Media Strategy

With a $2K+ budget, paid media should be concentrated around launch week for maximum impact, then sustained at a lower level through June. The split below puts the money where the target buyers are.

### Budget Allocation

| Platform | % of Budget | Est. Spend | Objective |
| --- | --- | --- | --- |
| LinkedIn Ads | 50% | $1,000+ | Reach distributors and agency decision-makers directly. Drive demo requests. |
| Meta (Facebook + Instagram) | 35% | $700+ | Retarget website visitors. Boost top-performing organic posts. Build awareness. |
| Reserve / Testing | 15% | $300+ | A/B test creative. Reallocate to whichever platform delivers better results mid-month. |

### Campaign Timeline

| Dates | Campaign | Platform | Notes |
| --- | --- | --- | --- |
| May 28–31 | Pre-launch teaser ads | LinkedIn + Meta | Build pixel data and warm audiences before launch day |
| June 1–7 | Launch campaign (heavy spend) | LinkedIn + Meta | 60% of total budget deployed this week for maximum impact |
| June 8–21 | Sustain campaign (moderate spend) | LinkedIn + Meta | Retarget website visitors + lookalike audiences. 30% of budget. |
| June 22–30 | Optimize and reallocate | Top performer | Shift remaining 10% to whichever platform is delivering better cost-per-lead |

### Targeting

LinkedIn: Job titles: Account Executive, Sales Director, VP of Sales at branded merchandise companies. Director of Events, VP of Experiential Marketing at activation agencies.

Meta: Website visitor retargeting (pixel must be live by May 20). Lookalike audiences built from demo request conversions. Interest-based targeting for event marketing professionals.

# 6. Content Creation Requirements

Based on the schedules above, here is the total content needed beyond the 10 existing teaser posts. Use this to scope the creative workload and plan production time.

| Content Type | Pre-Launch (58 days) | Launch Week | Post-Launch (Jun 8–30) | Total Needed |
| --- | --- | --- | --- | --- |
| LinkedIn posts | 12–14 new | 6 | 12–15 | 30–35 |
| Instagram feed posts / carousels | 16–20 new | 6 | 14–18 | 36–44 |
| Instagram Reels (15–60 sec video) | 8–10 | 3–4 | 8–10 | 19–24 |
| Instagram Stories | 6–8 | 5–7 | 4–6 | 15–21 |
| Facebook posts | 10–12 new | 5–6 | 8–10 | 23–28 |
| Email campaigns | 0–1 (pre-launch tease) | 3 | 6 | 9–10 |
| Press release | 0 | 1 | 0 | 1 |
| Blog / byline articles | 0 | 0 | 2–3 pitches | 2–3 |
| Sales deck (refreshed brand) | 1 (pre-refresh) + 1 (post-refresh) | 0 | 0 | 2 |
| One-pagers | 0–1 | 0 | 2 (distributor + agency) | 2–3 |
| Paid ad creative sets | 0 | 2–3 sets | 1–2 refresh sets | 3–5 sets |

Many Facebook posts are cross-posts from LinkedIn or Instagram, which reduces the unique creation burden. Instagram Stories can be lighter-weight production (polls, countdowns, behind-the-scenes footage) and do not require the same polish as feed posts.

# 7. Key Milestones and Deadlines

| Date | Milestone | Details |
| --- | --- | --- |
| Apr 4 | Pre-launch social posting begins | First of 10 teaser posts goes live on Instagram |
| Apr 4–May 1 | All 10 existing teaser posts deployed | Distributed across the Week 1–4 schedule |
| Apr 7–30 | Initial HALO AE and activation agency outreach | Personalized emails with product overview deck |
| May 1 | Countdown officially begins | "June 1 is the day" post goes live across all platforms |
| May 10–14 | Final brand refresh assets received | New logo, color palette, fonts, and guidelines from the design team |
| May 15 | Brand refresh goes live on social | Profile photos, banners, and bios updated across all three platforms |
| May 17–20 | Website updated with new brand | Refreshed visuals, updated copy, and launch landing page live |
| May 20 | Paid media tracking pixels verified | LinkedIn and Meta tracking confirmed and firing correctly |
| May 25 | All launch day content finalized | Social posts, email blast, press release, and ad creative locked |
| May 28 | Paid media campaigns loaded and scheduled | Ads ready to activate on June 1 |
| May 29 | Embargoed press release sent to media | Trade publications and local business press receive advance copies |
| June 1 | OFFICIAL LAUNCH DAY | All channels go live simultaneously |
| June 7 | Launch week performance review | Assess what is working. Adjust the June plan if needed. |
| June 14 | Mid-month pipeline review | Evaluate demo-to-opportunity conversion. Adjust outreach volume or messaging. |
| June 22–30 | Month-end push | Close early deals. Capture testimonials. Book Q3 activations. |
| June 30 | End-of-month review and July planning | Compile all metrics. Set the July content and outreach cadence. |

# 8. Success Metrics and KPIs

Track the following weekly during pre-launch and daily during launch week. These are the numbers that tell us whether the plan is working or needs adjustment.

## Social Media

| Metric | Pre-Launch Target (by May 31) | End of June Target |
| --- | --- | --- |
| LinkedIn followers | 200–500 | 750–1,000 |
| Instagram followers | 300–700 | 1,000–1,500 |
| Facebook page likes | 150–300 | 400–600 |
| Average engagement rate (all platforms) | 3–5% | 3–5% sustained |
| Link clicks to website (from social) | 100–200 total | 300–500 total |

## Lead Generation

| Metric | Pre-Launch Target | End of June Target |
| --- | --- | --- |
| Demo requests | 10–20 | 40–60 cumulative |
| Demos completed | 5–10 | 25–35 cumulative |
| Email list subscribers | 50–100 | 200–400 |
| Qualified opportunities in pipeline | 3–5 | 10–15 |

## Paid Media

| Metric | Target |
| --- | --- |
| Cost per click (LinkedIn) | $3–$8 |
| Cost per click (Meta) | $1–$3 |
| Cost per demo request (blended) | $30–$75 |
| Click-through rate (LinkedIn) | 0.5–1.0% |
| Click-through rate (Meta) | 1.0–2.5% |

## Revenue and Pipeline

| Metric | End of June Target |
| --- | --- |
| Signed LOIs or contracts | 2–5 |
| Total pipeline value (qualified opportunities) | Track and report |
| Average deal cycle from demo to close | Establish baseline |
| First live activation scheduled | 1–2 booked for July or August |